## Status Report
Status Report for Team #
Project |  | Status: (Red/Yellow/Green)
Date: | 2024-05-20 | Overall Status: | Green
Contact: | Mahir | Explanation: | I believe we are on track to finishing on time.
Prepared By: | Mahir
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Mahir | Created Model, Daos, Service layer and created the user and playlist controller.
Nikoleta | Wrote tests for Dao classes , Database ERD, Service layer
Ruaraidh | Created a frontend for adding tracks to a music playlist. Implemented the Spotify api to retreive tracks. Created flowchart
Abdullah
ID # | Key Issues | Action Plan |  |  | Status
1 | REST API | Create a User, song, artist controller |  |  | Yellow
2 | Accessing Javascript file | Application needs to be running to access file |  |  | Green
3 | Flowchart | Create a flowchart for the application |  |  | Green
4 | Testing the service layer/creating custom exceptions | Write custom exceptions for the service layer and do testing for it |  |  | Yellow
Critical Milestones |  | Health | Due Date | Comment/Status %
Database ERD |  | Green | 2024-05-20
DAOs |  | Green | 2024-05-20
Service Layer |  | Green | 2024-05-20
Unit testing |  | Green | 2024-05-20
Controller |  | Yellow | 2024-05-20 | Working on identifying what I require
Postman |  | Yellow | 2024-05-20 | Testing Controllers
Retrieving songs from spotify |  | Green | 2024-05-20
Adding the songs to a list |  | Green | 2024-05-20
Login portal/Dashboard |  | Yellow | 2024-05-20
Create a user (username/ password) |  | Green | 2024-05-20
Store/update users using REST API |  | Green | 2024-05-20
Password encoder |  | Green | 2024-05-20
Flowchart |  | Green | 2024-05-20
Class diagram |  | Yellow | 2024-05-20
Retrieving playlists from spotify |  |  | 2024-05-22
CRUD Operations on playlist |  |  | 2024-05-22
Storing/Uploading the playlist back with the spotify api |  |  | 2024-05-22
Wireframes prototype |  |  | 2024-05-22
Presentation |  |  | 2024-05-22
Documentation (comments) |  |  | 2024-05-22