## Status Report
Status Report for Team #
Project |  | Status: (Red/Yellow/Green)
Date: | 2024-05-21 | Overall Status: | Green
Contact: | Ruaraidh | Explanation: | we are on track to finishing on time.
Prepared By: | Ruaraidh
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Mahir | Created Model, Daos, Service layer and created the user controller.
Nikoleta | Wrote tests for Dao classes , Database ERD, service layer
Ruaraidh | Created a frontend for adding tracks to a music playlist. Implemented the Spotify api to retreive tracks. Created flowchart.
Ruaraidh | Added frontend for login and register screen.
Nikoleta | Added custom exceptions to the service layer and worked on testing it
Mahir | Adding songs/artist to the database through song controller and artist controller
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date | Comment/Status %
Database ERD |  | Green | 2024-05-20
DAOs |  | Green | 2024-05-20
Service Layer |  | Green | 2024-05-20
Unit testing |  | Yellow | 2024-05-23
Controller |  | Yellow | 2024-05-23
Postman |  | Yellow | 2024-05-23
Retrieving songs from spotify |  | Green | 2024-05-20
Adding the songs to a list |  | Green | 2024-05-20
Login portal/Dashboard |  | Yellow | 2024-05-23
Create a user (username/ password) |  | Green | 2024-05-20
Store/update users using REST API |  | Green | 2024-05-20
Password encoder |  | Green | 2024-05-20
Flowchart |  | Green | 2024-05-20
Class diagram |  | Yellow | 2024-05-21
Frontend register adds to user database |  | Green | 2024-05-21
Adding songs to the database |  | Green | 2024-05-21
Retrieving playlists from spotify |  |  | 2024-05-22
CRUD Operations on playlist |  |  | 2024-05-22
Storing/Uploading the playlist back with the spotify api |  |  | 2024-05-22
Wireframes prototype |  |  | 2024-05-23
Presentation |  |  | 2024-05-23
Documentation (comments) |  |  | 2024-05-23