## Status Report
Status Report for Team #
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2024-05-22 |  | Overall Status: | Green
Contact: | Nikoleta |  | Explanation: | we are on track to finishing on time.
Prepared By: | Nikoleta
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Mahir | Created Model, Daos, Service layer and created the user controller.
Nikoleta | Wrote tests for Dao classes , Database ERD, service layer
Ruaraidh | Created a frontend for adding tracks to a music playlist. Implemented the Spotify api to retreive tracks. Created flowchart.
Ruaraidh | Added frontend for login and register screen.
Nikoleta | Added custom exceptions to the service layer and worked on testing it
Mahir | Adding songs/artist to the database through song controller and artist controller
Nikoleta | Added a test database and worked on testing the dao and service layer
Ruaraidh | Added frontend for adding a playlist. Added login portal functionality.
Mahir | Testing the playlist controller, Service layer and updating the database model.
ID # | Key Issues |  | Action Plan |  |  | Status
1 | Unit testing | Tests do not run | Redo tests
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Database ERD |  |  | Green | 2024-05-20 | Done
DAOs |  |  | Green | 2024-05-20 | Done
Service Layer |  |  | Green | 2024-05-20 | Done
Unit testing |  |  | Yellow | 2024-05-23
Controller |  |  | Green | 2024-05-23 | Done
Postman |  |  | Green | 2024-05-23 | Done
Retrieving songs from spotify |  |  | Green | 2024-05-20 | Done
Adding the songs to a list |  |  | Green | 2024-05-20 | Done
Login portal/Dashboard |  |  | Green | 2024-05-23 | Done
Create a user (username/ password) |  |  | Green | 2024-05-20 | Done
Store/update users using REST API |  |  | Green | 2024-05-20 | Done
Password encoder |  |  | Green | 2024-05-20 | Done
Flowchart |  |  | Green | 2024-05-20 | Done
Class diagram |  |  | Green | 2024-05-21 | Done
Frontend register adds to user database |  |  | Green | 2024-05-21 | Done
Adding songs to the database |  |  | Green | 2024-05-21 | Done
Adding artists to the database |  |  | Green | 2024-05-21 | Done
Retrieving playlists from database |  |  | Green | 2024-05-22 | Done
CRUD Operations on playlist |  |  | Green | 2024-05-22 | Done
Storing the playlist to the database |  |  | Green | 2024-05-22 | Done
Wireframes prototype |  |  | Green | 2024-05-23
Presentation |  |  | Green | 2024-05-23
Documentation (comments) |  |  | Green | 2024-05-23