## Status Report
Status Report for Team 2
Project |  | Status: (Red/Yellow/Green)
Date: | 2024-05-22 | Overall Status: | Green
Contact: | Mahir | Explanation: | We are finished
Prepared By: | Mahir
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Mahir | Created Model, Daos, Service layer and created the user controller.
Nikoleta | Wrote tests for Dao classes , Database ERD, service layer
Ruaraidh | Created a frontend for adding tracks to a music playlist. Implemented the Spotify api to retreive tracks. Created flowchart.
Ruaraidh | Added frontend for login and register screen.
Nikoleta | Added custom exceptions to the service layer and worked on testing it
Mahir | Adding songs/artist to the database through song controller and artist controller
Nikoleta | Added a test database and worked on testing the dao and service layer
Ruaraidh | Added frontend for adding a playlist. Added login portal functionality.
Abdullah | Added CSS styling to make app visually appealing and aligned with Spotify theme
Mahir | Testing the playlist controller, Service layer and updating the database model.
Nikoleta | Finished unit tests and worked on the presentation
ID # | Key Issues | Action Plan |  |  | Status
1 | Spring Security (Stretch goal) | Restrict access to certain endpoints |  |  | Yellow
2 | Front end | Removing playlist |  |  | Resolved
Critical Milestones |  | Health | Due Date | Comment/Status %
Database ERD |  | Green | 2024-05-20 | Done
DAOs |  | Green | 2024-05-20 | Done
Service Layer |  | Green | 2024-05-20 | Done
Unit testing |  | Green | 2024-05-23 | Done
Controller |  | Green | 2024-05-23 | Done
Postman |  | Green | 2024-05-23 | Done
Retrieving songs from spotify |  | Green | 2024-05-20 | Done
Adding the songs to a list |  | Green | 2024-05-20 | Done
Login portal/Dashboard |  | Green | 2024-05-23 | Done
Create a user (username/ password) |  | Green | 2024-05-20 | Done
Store/update users using REST API |  | Green | 2024-05-20 | Done
Password encoder |  | Green | 2024-05-20 | Done
Flowchart |  | Green | 2024-05-20 | Done
Class diagram |  | Green | 2024-05-21 | Done
Frontend register adds to user database |  | Green | 2024-05-21 | Done
Adding songs to the database |  | Green | 2024-05-21 | Done
Adding artists to the database |  | Green | 2024-05-21 | Done
Retrieving playlists from database |  | Green | 2024-05-22 | Done
CRUD Operations on playlist |  | Green | 2024-05-22 | Done
Storing the playlist to the database |  | Green | 2024-05-22 | Done
Presentation |  | Green | 2024-05-23 | Done
Documentation (comments) |  | Green | 2024-05-23 | Done
Spring security (stretch goal) |  | Yellow | 2024-05-23 | 40%